## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
That User Story | Code Things…
Server implementation | Workout Generation (SS) | Jordan | 10 | 10 | 0 | 0 | 0
| Login authentication (SS) | Ben | 10 | 1 | 1 | 1 | 0
| Registration (SS) | Ben | 5 | 5 | 5 | 5 | 0
| Query sending (C) | All | 10 | 5 | 5 | 0 | 0
| Query handling (SS) | All | 10 | 5 | 5 | 0 | 0
| Porting model classes to Python (SS) | Jordan | 10 | 3 | 0 | 0 | 0
| Server/Client serialization/deserialization (C) -> (SS) | Jordan | 5 | 8 | 8 | 0 | 0
Set intensity level for workout | Update GUI (C) | Tyler | 1 | 1 | 0 | 0 | 0
| Update wireframes | Tyler | 1 | 1 | 1 | 1 | 0
| Update Preferences class (C) -> (SS) | Tyler | 1 | 1 | 0 | 0 | 0
| Update workout generation to include intensity (SS) | Jordan | 1 | 3 | 3 | 3 | 0
| Modify exercises database to hold intensity value (C) -> (SS) | Jordan | 1 | 1 | 0 | 0 | 0
| Intensity Enum (C) | Tyler | 1 | 1 | 1 | 1 | 0
Register new user | Make a register button in LoginUI (C) | Ben | 1 | 1 | 1 | 1 | 0
| Bind event to send info to server (SS) | Ben | 1 | 2 | 2 | 2 | 0
| Don't allow duplicates (SS) | Ben | 3 | 2 | 2 | 2 | 0
Change view implementation for Exercise Details | Accordion /multi-window from drop down (C) | Ben | 5 | 3 | 3 | 0 | 0
|  | Estimate Totals | 76 | 53 | 37 | 16 | 0