## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
User login | Create User class - Preferences, Calendar, Login credentials | Tyler | 1
| Implement Login page UI | Tyler | 2
| Login authentication interface | Ben | 1 | 1 | 0 | 0
| Dummy login class | Ben | 1 | 1 | 0 | 0
| Preferences class - list of selected days and muscle groups | Jordan | 1
| Calendar class - hashmap of day/workout pairs | Jordan | 1
| I/O interface - load() and save() | Ben | 1 | 1 | 1 | 1
| Dummy loader class - FileWriter, FileReader | Ben | 2 | 2 | 2 | 2
Workout preference | Day Enum | Tyler | 1
| Implement Preferences indication UI | Tyler | 1
| UI data binding for Preferences class | Tyler | 1
| MuscleGroup Enum | Tyler | 1
Weekly schedule view | Implement week view UI | Ben | 1 | 1 | 1 | 0
| Calendar data binding | Ben | 1 | 1 | 1 | 1
Workout generation | WorkoutGenerator class - API query handler, "intelligent" workout programming | Jordan | 2
| Workout class - collection of Exercises | Ben | 1 | 1 | 1 | 1
| Exercise class - fields populated by WorkoutGenerator API queries | Jordan | 1
Workout detail view | Implement daily workout detail view UI | Tyler | 1
| Implement Exercise detail UI | Jordan | 1
| Estimate Totals |  | 22 | 8 | 6 | 5 | 0