## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Update documentation | All | 2
| Change control flow after login to show day workout | Ben | 1
Track user progress | Update DailyDetailView to include workout duration feedback | Tyler | 1
| Add StatsTracking class (CS, SS) | Jordan | 1
| Fitness points over time - update on workout completion | Tyler | 1
| Bodyweight over time | Ben | 1
| Add fitness points field for exercises in JSON | Jordan | 1
| Add rep setting to WorkoutGenerator | Jordan | 3
Adjust workout generation | Add field for effortLevel in Workout (Reps*fitness points) (CS, SS) | Ben | 1
| Add fitness point threshold to Intensity enum | Jordan | 1
UI for progress tracking | Update documentation | All | 2
| Add chart for change in bodyweight over time | Tyler | 2
| Add chart for fitness capacity over time | Ben | 2
| Add field for average workout duration time | Ben | 1
| Add field for bodyweight update - send info automatically to server, update chart client-side | Tyler | 3
| Create StatsPage UI | Ben | 2
| Update documentation | All | 2
| Estimate Totals |  | 27 | 0 | 0 | 0 | 0