## Sheet1
Related User Story | Task Description | Team Member | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Login | Update documentation | All | 2 | 2 | 2 | 2 | 0
| Change control flow after login to show day workout | Ben | 1 | 1 | 1 | 0 | 0
Track user progress | Update DailyDetailView to include workout duration feedback | Tyler | 1 | 1 | 0 | 0 | 0
| Add StatsTracking class (CS, SS) | Jordan | 1 | 1 | 0 | 0 | 0
| Fitness points over time - update on workout completion | Tyler | 1 | 1 | 0 | 0 | 0
| Bodyweight over time | Ben | 1 | 1 | 1 | 1 | 0
| Add fitness points field for exercises in JSON | Jordan | 1 | 1 | 0 | 0 | 0
| Add rep setting to WorkoutGenerator | Jordan | 3 | 3 | 1 | 0 | 0
Adjust workout generation | Add field for intensity (CS, SS) | Jordan | 1 | 1 | 0 | 0 | 0
| Add fitness point threshold to Intensity enum | Jordan | 1 | 1 | 0 | 0 | 0
UI for progress tracking | Add chart for change in bodyweight over time | Tyler | 2 | 2 | 0 | 0 | 0
| Add chart for fitness capacity over time | Tyler | 2 | 2 | 0 | 0 | 0
| Add field for workout duration time | Ben | 1 | 1 | 1 | 1 | 0
| Add field for bodyweight update | Tyler | 1 | 1 | 0 | 0 | 0
| Create StatsPage UI | Tyler | 1 | 1 | 0 | 0 | 0
| Wire StatsUI Graphs and data | Ben | 1 | 1 | 1 | 1 | 0
| Estimate Totals |  | 21 | 21 | 7 | 5 | 0